## Sheet1
Week | ML Application | Difficulty
2021-04-01 | Gather requirements | Medium
2021-04-08 | Plan the scenarios that should work | Medium
2021-04-15 | Setup user accounts and infrastructure | Medium
2021-04-22 | Create Makefile for build automation | Easy
2021-04-29 | Finalize on test, linting tools | Easy
2021-05-06 | Write tests with hard coded values | Easy
2021-05-13 | Complete Design review for the system | Medium
2021-05-20 | Implement initial code with tests | Medium
2021-05-27 | Finish implementing code | Hard
2021-06-03 | Demo to the stakeholders | Easy
2021-06-10 | Apply feedback | Medium
2021-06-17 | Put application to production | Hard
Goals
Build a ML application for prediction
No onpremise maintenace, everything on cloud
Write tests
Build CI/CD pipeline
Have a working code always
Q2 plan | Finish implmenting the application and put into production
Yearly plan | Maintenance of the application and do marketing around it